## Example
SEO Roadmap
Action Item/Task | Person Responsible | Tools Needed | Progress | January | February | March | April | May | June | July | August | September | October | November | December
Skyscraper Link Building Campaign
Audit website backlink profile | John Miller | SEOptimer | Done
Shortlist link prospects | John Miller | SEoptimer | Done
Find contact information for link prospects | John Miller | Hunter.io | In progress
Write link-building email outreach copy | Cara Donaldson |  | In progress
Set up link-building campaign in Lemlist | John Miller | Lemlist | Not started
Content Production for Blog
Use keyword research tool to find keyword opportunities [ x 10] | John Miller | SEOptimer | Done
Create content briefs [ x 10] | John Miller |  | Done
Send content briefs to senior content manager | Cara Donaldson |  | Done
Send content briefs to writers | Cara Donaldson |  | Done
Review drafts and provide feedback | Mary Stevens |  | In progress
Upload content to WordPress [follow "Content Upload SOP"] | John Miller |  | Not started
Publish content | Mary Stevens |  | Not started
On-Page SEO Optimization
Audit on-page SEO | John Miller | SEOptimer | Done
Add title tag to site | John Miller |  | In progress
Write meta-description and add to website | Cara Donaldson |  | Done
Optimize on-page images | Peter Samuels |  | Not started
Minify HTML, Javascript, and CSS files | Peter Samuels |  | Not started
Reduce page size | Peter Samuels |  | In progress

## Template
SEO Roadmap
Action Item/Task | Person Responsible | Tools Needed | Progress | January | February | March | April | May | June | July | August | September | October | November | December